## Project Planner
Project Planner
Period = Day of the month. April, then May |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [15 empty] | Actual Duration
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
Log In (plan) | 22 | 3 | bar: PERIODS 22 to PERIODS 24
(actual) |  |  | 23 | 3 | 100% | bar: PERIODS 23 to PERIODS 25
Sign Up (plan) | 23 | 3 | bar: PERIODS 23 to PERIODS 25
(actual) |  |  | 24 | 3 | 100% | bar: PERIODS 24 to PERIODS 26
Log Out (plan) | 22 | 2 | bar: PERIODS 22 to PERIODS 23
(actual) |  |  | 25 | 2 | 100% | bar: PERIODS 25 to PERIODS 26
View Notes (plan) | 23 | 5 | bar: PERIODS 23 to PERIODS 27
(actual) |  |  | 26 | 8 | 100% | bar: PERIODS 26 to PERIODS 3
Delete Note (plan) | 23 | 5 | bar: PERIODS 23 to PERIODS 27
(actual) |  |  | 26 | 8 | 100% | bar: PERIODS 26 to PERIODS 3
View Tasks (plan) | 25 | 4 | bar: PERIODS 25 to PERIODS 28
(actual) |  |  | 26 | 8 | ?% | bar: PERIODS 26 to PERIODS 3
Delete task (plan) | 25 | 4 | bar: PERIODS 25 to PERIODS 28
(actual) |  |  | 26 | 8 | ?% | bar: PERIODS 26 to PERIODS 3